## Sheet1
RISK REGISTER
Project Name |  | Revamping Online Menu - DSpot
# | Risk | Risk Description | Prob | Imp | Risk Score | Risk Response Type | Risk Response Plan (Plan A) | Contingency Plan (if plan A don't work, Plan B)
1 | Design Misalignment | The new menu does not align with the brand identity or customer preferences | 0.5 | 10 | 5 | Avoid | Validate the design from focus groups or conduct surveys before the implementation | Use the feedback to adjust the design, and to update the menu later
2 | Data Loss | The loss of menu data or customer data during system updates or migrations. | 0.2 | 10 | 2 | Mitigate | Backup all data before making changes to the menu | Restore from the backup and ensure customer trust through communication
3 | Poor user experience | Customers find it difficult to use or navigate, and is not designed with accessibility in mind leading to fewer engagement | 0.8 | 8 | 6.4 | Mitigate | Conduct usability testing to ensure ease of navigation and clarity | Add user-friendly features like tutorials or highlight key menu sections.
4 | Delay in Launch | Unexpected delays in the revamp process due to dependencies (eg. vendor issues, staffing, or approvals) | 0.5 | 5 | 2.5 | Mitigate | Set clear deadlines and track progress using project management tools | Launch a temporary version with basic features while finalizing updates.
5 | Over Budget | The costs exceeds the overall calculated budget due to unseen expenses like additional software tools | 0.5 | 8 | 4 | Mitigate | Monitor expenses and track all costs during the project regularly | Scale down features and prioritize the most impactful updates.
6 | Not meeting core requirements | The new menu is implemented without meeting the requirements of the user stories or acceptance criteria | 0.2 | 10 | 2 | Avoid | Ensure the website is implemented with the user stories and acceptance criteria in mind. | Hold meetings to discuss project progress to ensure that the requirements are met.
7 | Digital Display Errors | Incorrect prices or item descriptions on the digital meny could cause customer dissatisfaction and loss of trust | 0.5 | 8 | 4 | Mitigate | Regularly review and update digital menu content to ensure accuracy. | Implement customer feedback mechanisms to quickly resolve errors.
8 | Seasonal Flavor Avaibility Issues | Failure to plan inventory for seasonal flavors might lead to stockouts, negatively affecting customer experience. | 0.2 | 8 | 1.6 | Mitigate | Monitor demand trends and adjust inventory planning for seasonal flavors. | Offer alternative flavors or discounts if seasonal items are unavailable.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0