## ProjectSchedule
Revamping Online Menu
Company Name: DSpot |  | Schedule Start: |  | 2024-11-08
Project Manager: Sukhman Hara |  | Display Week: |  | 1
|  |  | Work Week: | 7 Day |  |  |  | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31
 | time axis 2024-11-04 to 2025-04-06
ACTIVITY | ASSIGNED TO | DUR (days) | PROGRESS | START | END | Column1 | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
#VALUE!
Sprint 1: Desert search and reviews |  | 15 |  |  |  | #VALUE!
Implement views for reviews and ratings for desserts. |  | 5 | 0% | 2024-11-08 | 2024-11-12 | 2024-11-12
Create design that includes the number of reviews and stars that are filled based on the type of reviews it gets. | [5 empty] | #VALUE!
Create an API that fetches the reviews for a dessert. | [5 empty] | #VALUE!
Implement the design. | [5 empty] | #VALUE!
Implement views for images and names of the deserts |  | 5 | 0% | 2024-11-13 | 2024-11-17 | 2024-11-17
Create a design that showcases the desserts. | [5 empty] | #VALUE!
Create an API that fetches the the images and names of the desert. | [5 empty] | #VALUE!
Connect front end to our back-end API | [5 empty] | #VALUE!
Implement design | [5 empty] | #VALUE!
Test backend functionality and ensure that the fetched data is displayed in accordance to the design | [5 empty] | #VALUE!
Implement search functionality |  | 5 | 0% | 2024-11-18 | 2024-11-22 | 2024-11-22
Create design for the search bar | [5 empty] | #VALUE!
Create an API that fetches the data that the user searches for. | [5 empty] | #VALUE!
Connect front end to our back-end API | [5 empty] | #VALUE!
Test search functionality with different input | [5 empty] | #VALUE!
Sprint 2: Implement personalization of the menu and filter |  | 15 |  |  |  | #VALUE!
Implement special promotions or discounts |  | 5 | 0% | 2024-11-23 | 2024-11-27 | #REF!
Create UI/ UX and design wireframes and visual mockups for the discount and promotion element | [5 empty] | #REF!
Create API endpoints for CRUD operations for Promotions | [5 empty] | #REF!
Implement filter functionality |  | 5 | 0% | 2024-11-28 | 2024-12-02 | 2024-12-02
Design the filter UI elements (dropdown, checkboxes, sliders etc)
Implement filter logic on frontend: Connect the filter UI to the API
Implement personalized recommendations on my menu feed based |  | 5 | 0% | 2024-12-03 | 2024-12-07 | 2024-12-07
Integrate an algorithm to generate personalized recommendations | [5 empty] | #VALUE!
Build an API endpoint to serve recommendations based on each user's data | [5 empty] | #VALUE!
Design the layout and visual elements of the recommendations section on the menu feed | [5 empty] | #VALUE!
Sprint 3: Enhanced Product Customization and Filtering |  | 15 |  |  |  | #VALUE!
Implement filtering products based on attributes like price and size |  | 5 | 0% | 2024-12-08 | 2024-12-12 | 2024-12-12
UI for filtering options where users can select attributes like price range & size. | [5 empty] | #VALUE!
Develop API endpoints or backend logic to handle filtering | [5 empty] | #VALUE!
Connect UI to Backend, ensuring that selecting filters dynamically updates the product list. | [5 empty] | #VALUE!
Conduct testing to verify that filters work correctly across various scenarios and edge cases | [5 empty] | #VALUE!
Implement customizing ice cream with different toppings |  | 5 | 0% | 2024-12-13 | 2024-12-17 | 2024-12-17
UI that allows customers to select from a list of toppings, showing visuals for each topping option. | [5 empty] | #VALUE!
backend for custom toppings, including tracking selected toppings & calculating the final price. | [5 empty] | #VALUE!
Implement logic to update the total price dynamically on the frontend based on toppings. | [5 empty] | #VALUE!
Test the entire customization process | [5 empty] | #VALUE!
Implement viewing the description and ingredients of the ice-cream |  | 5 | 0% | 2024-12-18 | 2024-12-22 | 2024-12-22
Update the database schema to include fields for description & ingredients for each product, and populate this data. | [5 empty] | #VALUE!
UI that displays the ice cream's description, ingredients, & other relevant details. | [5 empty] | #VALUE!
logic to fetch description & ingredient information from the backend & display it on the product details page. | [5 empty] | #VALUE!
Test that all description and ingredient information is correctly displayed across devices | [5 empty] | #VALUE!
Sprint 4: the popular desert and allergens |  | 15 |  |  |  | #VALUE!
Implement Functionality to View the Most Popular Desserts |  | 5 | 0% | 2024-12-23 | 2024-12-27 | 2024-12-27
display the top 5 - 10 most popular deserts | [5 empty] | #VALUE!
dynamically update popular desserts based on users' past orders. | [5 empty] | #VALUE!
the popular desserts can be accessed from the homepage or menu | [5 empty] | #VALUE!
Conduct testing to verify that filters work correctly across various scenarios and edge cases | [5 empty] | #VALUE!
Implement Functionality to Warn Customers with Allergens Such as Peanuts or Gluten |  | 5 | 0% | 2024-12-28 | 2025-01-01 | 2025-01-01
the warning for allergens must be clear and visually noticable on dessert items. | [5 empty] | #VALUE!
display the warning labels near the desert name and in the detail description | [5 empty] | #VALUE!
display a pop up that show information about the allgergen warning when users hover over the allergen label | [5 empty] | #VALUE!
Sprint 5: |  | 15 |  |  |  | #VALUE!
Implement a Deleting items functionality |  | 5 | 0% | 2025-01-02 | 2025-01-06 | 2025-01-06
design a UI for delete functionality and decide what changes can be made | [5 empty] | #VALUE!
Develop API endpoints or backend logic to handle delete function | [5 empty] | #VALUE!
Connect UI to Backend, that deletes items or subitems from the product list. | [5 empty] | #VALUE!
Conduct testing to verify that filters work correctly across various scenarios and edge cases | [5 empty] | #VALUE!
Implement a adding items functionality |  | 5 | 0% | 2025-01-07 | 2025-01-11 | 2025-01-11
design a UI for addfunctionality and decide what changes can be made | [5 empty] | #VALUE!
Develop API endpoints or backend logic to handle add items function | [5 empty] | #VALUE!
Connect UI to Backend, that adds items or subitems from the product list. | [5 empty] | #VALUE!
Conduct testing to verify that filters work correctly across various scenarios and edge cases | [5 empty] | #VALUE!
Sprint 6: |  | 15 |  |  |  | #VALUE!
Final UI/UX Review |  | 5 | 0% | 2025-01-12 | 2025-01-16 | 2025-01-16
Visual Consistency Check | [5 empty] | #VALUE!
Functionality and Usability Testing | [5 empty] | #VALUE!
Responsiveness and Device Compatibility | [5 empty] | #VALUE!
Final Accessibility and Compliance Audit | [5 empty] | #VALUE!
Performance Testing |  | 5 | 0% | 2025-01-17 | 2025-01-21 | 2025-01-21
Define Performance Metrics and Benchmarks | [5 empty] | #VALUE!
Load Testing | [5 empty] | #VALUE!
Stress Testing and Edge Case Handling | [5 empty] | #VALUE!
Monitoring and Reporting Results | [5 empty] | #VALUE!
Documentation Finalization |  | 5 | 0% | 2025-01-22 | 2025-01-26 | 2025-01-26
User Guide Documentation | [5 empty] | #VALUE!
API Documentation | [5 empty] | #VALUE!
Developer Setup and Configuration | [5 empty] | #VALUE!
Performance and Testing Documentation | [5 empty] | #VALUE!
Deployment to Staging Environment |  | 5 | 0% | 2025-01-27 | 2025-01-31 | 2025-01-31
Prepare Staging Environment | [5 empty] | #VALUE!
Deploy Code and Database Migrations | [5 empty] | #VALUE!
Perform Functional Testing in Staging | [5 empty] | #VALUE!
Monitor and Log Staging Deployment | [5 empty] | #VALUE!
Insert new rows ABOVE this one | [5 empty] | #VALUE!